Print and email invitations should be sent/mailed 5-6 weeks prior to the event. To meet that target, your action items are 10 weeks and 8 weeks before the event as shown below:

Your Print Invitation Deadlines (10 weeks before event):

10 weeks before event: Request preliminary count and mailing lists and give marketing team all the information they need to ensure the printed invitation goes out on time.

- Submit list requests

- Request preliminary list count: Make "Request Due Date" 9 weeks before event

- Request mailing list: Make "Estimated Mailing Date" 7 weeks before event

- Submit StratComm job request

- Fill out the Event Invitation Template document and put it in our Project Intake folder when submitting your request

Your Email Invitation Deadlines (8 weeks before event):

8 weeks before event: Request email lists and give data team all the information they need to ensure your email invitations go out on time.

- Submit list requests

- For initial email request: Make "Estimated Emailing or Calling Date" 5-6 weeks out from event

- For follow-up email request: Make "Estimated Emailing or Calling Date" 2 weeks out from event

- Submit content to data team at folder link you receive when you schedule your email

- Submit StratComm job request only if there is no print piece and a graphic is needed

Here are Production Timelines:

- Print:

- 1 week design/write

- 1 week for you to approve/review preliminary count list from data team

- 1-2 weeks to print; within this window you have 1 week to review mailing list from data team

- 2 days for distribution to drop in the mail

- Email:

- 1 week for StratComm to produce email header graphic, if one is needed

- 1 week for data team to build email